## TRACKER
Serial Number | Name of file | In RFP as in / Supporting Doc | What the File is about | PRIORITY | Current Status | RAG | Action Items | Assigned To | ETA | Comments | Risks and Issues
11 | Project_Plan-12 month.html | Add to RFP as is | A potential high-level project plan or timeline covering a 12-month period. | CRITICAL | IN PROGRESS | Amber | JM, KW, SA to review and sign off Max to review and approve | James, Kenny, Sim | TBD | Provides a roadmap view. | Timeline may be aggressive/unrealistic. Dependencies not mapped.
12 | Budget_Financial_Mgmt_Plan.html | Supporting Document | Plan detailing project budget, cost tracking, financial reporting, and funding management. | CRITICAL | Needs Review | Amber | Finalize Budget Numbers, Setup Tracking | Francis, Max to review and provide input | TBD | Essential for project financial health. | Budget constraints. Inaccurate cost tracking.
17 | Architecture.html | Add to RFP as is | Describes the proposed high-level technical architecture for the solution. | CRITICAL | Needs Review | Amber | Review, add architecture diagrams, finalize any other architectural detail and system design items and put it in this document | James, Kenny, Sim, Arun | TBD | Core technical design document. | Architecture may not meet scalability, reliability, or security NFRs.
19 | Solution_Functional_Non Functional.html | Add to RFP as is | Document likely summarizing the key functional and non-functional requirements or how the solution addresses them. | CRITICAL | Needs Review | Amber | Review for gaps and tweak as required and add diagrams etc | James, Kenny | TBD | Should align with RTM. | May miss requirements or conflict with detailed RTM.
32 | Requirements_Fulfillment_Mapping.html | Add to RFP as is | Likely a document mapping RFP requirements to proposed solution features or components (similar to RTM). | CRITICAL | Needs Review | Amber | Validate against Generated RTM, Ensure Completeness | Business Analyst/PM | TBD | Crucial for demonstrating compliance. Should align with my generated RTM. | May contain gaps or inaccuracies in mapping. Could conflict with RTM generated in previous step.
2 | Data_governance_compliance_controls_plan.html | Add to RFP as is | Plan detailing data governance policies, compliance requirements (e.g., FERPA), and control mechanisms. | HIGH | Needs Review | Amber | Review, Add Specific Controls | Compliance Lead | TBD | Covers key areas from RFP NFRs. | Requires legal/compliance expert review.
4 | Project_Implementation_Game_Plan.html | Supporting Document | Overall plan for implementing the project, potentially covering phases, milestones, and approach. | HIGH | Needs Review | Amber | Align with Specific Plans, Add Dates | Project Manager | TBD | Central implementation document. Decided that this will be supporting document for 12 month project plan | May overlap/conflict with other detailed plans.
5 | DataEngineering_Analytics_Reporting_ML_AI_Strategy.html | Supporting Document | Strategy covering data engineering pipelines, analytics, reporting tools, and potential ML/AI applications. | HIGH | Draft | Amber | Detail Tools/Tech, Define Use Cases | Data Lead | TBD | Covers reporting requirements. | ML/AI scope may be ambitious initially.
7 | Project_And_Change_And_Risk_Management_Plan.html | Supporting Document | Integrated plan covering project management approach, change control process, and risk management framework. | HIGH | Needs Review | Amber | Detail Change Process, Populate Risk Register | Project Manager | TBD | Consolidated key PM processes. | Requires active maintenance (esp. risks).
9 | Detailed_SDLC.html | Supporting Document | Describes the specific Software Development Lifecycle (SDLC) methodology, phases, and deliverables. | HIGH | Needs Review | Amber | Align with DevOps/Test Plans | Kenny W | TBD | Defines how software will be built. | Needs team buy-in and adherence.
13 | Security_Strategy.html | Add to RFP as is | Overall strategy addressing information security requirements, controls, compliance, and threat management. | HIGH | Needs Review | Amber | Align with RFP NFRs, Detail Controls | arkumar.cyb@gmail.com Arlenee Lopez-Ferguson | TBD | Addresses critical RFP security NFRs. | Needs thorough review and validation against policies (NYC3, OTI, etc.).
15 | User_Onboarding_Training_Comms_Strategy.html | Add to RFP as is | Strategy covering user onboarding processes, training delivery plan, and related communications. | HIGH | Needs Review | Amber | Detail Training Content/Schedule | Training Lead/Change Manager | TBD | Addresses RFP Sec 3.23. | Scale of training required is immense (RFP Sec 3.23.1).
20 | Team_Structure_And_Processes_Plan.html | Add to RFP as is | Describes the proposed project team structure, roles, responsibilities, and internal team processes. | HIGH | Needs Review | Amber | Finalize Roles, Align with Org Chart | Project Manager/Lead | TBD | Defines how the project team operates. | Unclear roles or inefficient processes proposed.
24 | Observability_Monitoring_IncidentManagement.html | Add to RFP as is | Strategy covering system observability, monitoring tools/metrics, and the incident management process for technical issues. | HIGH | Draft | Amber | Select Tools, Define Key Metrics, Detail IM Process | Ops Lead/SRE | TBD | Critical for operational stability & NFRs. | Monitoring may be insufficient. Incident process unclear or slow.
27 | GIS_Data_Mgmt_Integration_Strategy.html | Supporting Document | Specific strategy detailing how Geographic Information System (GIS) data will be managed, integrated, and utilized. | HIGH | Needs Review | Amber | Detail LION Integration, Define Update Process | GIS Specialist/Data Lead | TBD | Covers requirements like RFP Sec 3.2.5. | Complexity of integrating/maintaining various GIS data sources. Accuracy issues.
30 | Development_Strategy.html | Add to RFP as is | Outlines the overall strategy for software development, potentially covering methodologies, standards, tools. | HIGH | Needs Review | Amber | Align with SDLC, DevOps, Security Plans | Tech Lead | TBD | High-level development approach. | May conflict with more detailed plans (SDLC, DevOps).
33 | Test_Strategy.html | Add to RFP as is | Outlines the overall approach to testing, including levels (unit, integration, UAT), types, environments, and tools. | High | Needs Review | Amber | Detail Test Cases, Define Environments | QA Lead | TBD | Covers testing NFRs (RFP 3.25.32). | Test coverage may be insufficient. Lack of appropriate test environments/data.
8 | Advanced_Enhanced_User_Adoption_Strategy.html | Supporting Document | Plan focusing on strategies beyond basic training to drive deep user adoption and value realization. | LOW | Draft | Amber | Define Specific Tactics, Metrics | Change Manager | TBD | Goes beyond standard training plan. | May require dedicated resources/budget.
10 | Cloud_Cost_Mgmt_FinOps_Strategy.html | Supporting Document | Strategy for managing cloud costs, implementing FinOps practices, budgeting, and reporting on cloud spend. | LOW | Draft | Amber | Define Tagging Strategy, Setup Budget Alerts | Cloud Architect/PM | TBD | Important if using cloud infrastructure. | Cloud costs can escalate if not managed.
18 | Terraform_another_view.html | Supporting Document | Potentially an alternative perspective or specific detail related to Terraform infrastructure setup. | LOW | Draft | Amber | Review, Consolidate with Main Infra Plan | DevOps/Cloud Team | TBD | Relates to IaC. | Potential redundancy or conflict with other Terraform docs.
31 | Terraform_Infra_Setup_Guide.html | Supporting Document | A guide detailing the steps or configuration for setting up infrastructure using Terraform (Infrastructure as Code). | LOW | Draft | Amber | Review/Test Scripts, Document Variables | DevOps/Cloud Team | TBD | Specific IaC implementation guide. | Scripts may contain errors or security issues. Needs version control.
1 | DevOps_Strategy.html | Add to RFP as is | Outlines the strategy for DevOps practices, tools, and culture for the project. | MEDIUM | Draft | Amber | Review, Refine, Integrate | DevOps Lead | TBD | Initial draft generated. | Needs alignment with other plans (SDLC, Security).
3 | User_Transition_and_Cutover_Strategy.html | Supporting Document | Strategy for migrating users to the new system, including cutover planning. | MEDIUM | Draft | Amber | Detail Cutover Steps, Align with Training | Project Manager | TBD | High-level strategy outlined. | Needs detailed timings and rollback plan.
6 | Communications_Governance_Reporting_Strategy.html | Supporting Document | Plan for project communications, governance structure, and status reporting cadences/formats. | MEDIUM | Needs Review | Amber | Define Stakeholders, Finalize Cadence | Project Manager | TBD | Crucial for stakeholder management. | Needs clear buy-in on governance model.
14 | Hardware_Lifecycle_Logistics_Mgmt_Plan.html | Add to RFP as is | Plan for managing GPS device hardware lifecycle, including procurement, deployment, maintenance, and disposal logistics. | MEDIUM | Draft | Amber | Detail Maintenance/Replacement Process | Operations Lead | TBD | Covers requirements from RFP Sec 3.19. | Logistical complexity of managing 11k+ devices.
16 | Competitive Advantage Through Engineering Excellence.html | Supporting Document | Document likely outlining principles or strategies for achieving high-quality engineering outcomes. | MEDIUM | Draft | Amber | Review, Align with SDLC/DevOps | Tech Lead | TBD | Focuses on engineering quality. | May be high-level principles needing actionable steps.
21 | Compliance_Audit_Strategy.html | Add to RFP as is | Strategy outlining how compliance will be maintained and how audits (internal/external) will be handled. | MEDIUM | Draft | Amber | Define Audit Procedures, Align with Governance | mzinner@sentryms.com | TBD | Supports ongoing compliance. | Audit process may be insufficient or disruptive.
22 | DevOps_Detailed.html | Supporting Document | Provides more specific details on the DevOps strategy, possibly including CI/CD pipeline specifics. | MEDIUM | Draft | Amber | Define Toolchain, Detail Pipeline Stages | DevOps Lead | TBD | Complements DevOps_Strategy.html. | Proposed pipeline may be complex or inefficient. Tool choices need validation.
23 | SDLC_Detail_Implementation.html | Supporting Document | Focuses on the implementation details of the chosen SDLC, phase gates, specific activities. | MEDIUM | Needs Review | Amber | Validate against Detailed_SDLC.html, Add Metrics | Tech Lead/PM | TBD | Implementation view of SDLC. | Implementation details may not align with overall SDLC or team capacity.
25 | Formal_Project, Change, and Risk_Management_Plan.html | Supporting Document | Appears to be a more formal version or iteration of the integrated PM plan (similar to #7). | MEDIUM | Needs Review | Amber | Consolidate/Reconcile with #7, Finalize Processes | Project Manager | TBD | Potential duplicate/update of #7. | Confusion/conflict if not reconciled with other PM plan.
26 | Vendor_3rdParty_mgmt_logistics_plan.html | Supporting Document | Plan for managing relationships, performance, and logistics related to third-party vendors or subcontractors. | MEDIUM | Draft | Amber | Identify Key Vendors, Define SLAs/KPIs | Project Manager/Procurement | TBD | Important if relying on subcontractors. | Poor vendor performance impacting project. Lack of clear oversight.
28 | Innovation_Showcase.html | Supporting Document | Document potentially highlighting innovative aspects of the proposed solution or approach. | MEDIUM | Draft | Amber | Review, Extract Key selling points | Sales/Proposal Lead | TBD | Likely for proposal marketing/differentiation. | Claims of innovation may not be substantial or relevant.
29 | Operational_Excellence_BCP_DR_Plan.html | Supporting Document | Plan focusing on achieving operational excellence, likely incorporating Business Continuity and Disaster Recovery details. | MEDIUM | Needs Review | Amber | Align with BCP NFRs (3.27), Detail DR Procedures | Ops Lead | TBD | Includes BCP/DR elements (RFP 3.27). | DR plan untested or insufficient RTO/RPO.